## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Aditya Gupta | 2026-01-10 | Vectorstore file lock error during re-indexing | Sprint 2 | Aditya Gupta | Logical | Implemented hash-based persistent indexing | 2026-01-12 | Closed | Resolved Chroma file access conflict
2 | Aditya Gupta | 2026-01-18 | Duplicate chat history causing inconsistent responses | Sprint 3 | Aditya Gupta | Logical | Refactored session state update logic | 2026-01-19 | Closed | Ensured single source of chat history update
3 | Aditya Gupta | 2026-01-22 | Slow initial document indexing for large PDFs | Sprint 3 | Aditya Gupta | Maintainability | Optimized chunk size and overlap parameters | 2026-01-23 | Closed | Improved embedding efficiency
4 | Aditya Gupta | 2026-02-01 | Follow-up suggestions showing header text | Sprint 4 | Aditya Gupta | User Interface | Added filtering logic for LLM output | 2026-02-03 | Closed | Removed unwanted introductory lines
5 | Aditya Gupta | 05-02-206 | Inconsistent source ranking display UI | Sprint 4 | Aditya Gupta | User Interface | Simplified to single minimal source display | 2026-02-06 | Closed | Improved UI clarity and usability

## Sheet2
Logical
User Interface
Maintainability
Standards
Others