## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Upload and parse PDF documents | Must |  | Aditya Gupta | Completed
Sprint 1 | Sprint 1 | US-02 | Implement text chunking and embeddings | Must | US-01 | Aditya Gupta | Completed
Sprint 2 | Sprint 2 | US-03 | Implement similarity-based retrieval | Must | US-02 | Aditya Gupta | Completed
Sprint 2 | Sprint 2 | US-04 | Display source citation (filename + page) | Must | US-03 | Aditya Gupta | Completed
Sprint 3 | Sprint 3 | US-05 | Add multi-document upload support | Should | US-01 | Aditya Gupta | Completed
Sprint 3 | Sprint 3 | US-06 | Implement streaming LLM responses | Should | US-03 | Aditya Gupta | Completed
Sprint 4 | Sprint 4 | US-07 | Add AI study tools (summary, quiz, notes) | Could | US-03 | Aditya Gupta | Completed
Sprint 4 | Sprint 4 | US-08 | Implement smart follow-up suggestions | Could | US-03 | Aditya Gupta | Completed
Sprint 4 | Sprint 4 | US-09 | Add explanation-level selector (Beginner/Expert mode) | Could | US-03 | Aditya Gupta | Planned
Sprint 4 | Sprint 4 | US-10 | Implement query analytics dashboard | Could | US-03 | Aditya Gupta | Planned
Sprint 4 | Sprint 4 | US-11 | Enable clickable source navigation feature | Could | US-04 | Aditya Gupta | Planned
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7